## Project Plan
Minnesota Health Care Financing Task Force Project Plan | Revised 11/8/15
TASK | LEAD | STATUS | NOTES | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07 | 2015-12-14 | 2015-12-21 | 2015-12-28 | 2016-01-04 | 2016-01-11
Meetings
Health Care Financing Task Force | DHS | In-progress |  |  | 2015-10-02 |  |  | 2015-10-23 |  |  | 2015-11-13 |  |  | 2015-12-04 |  | 2015-12-18 |  |  | 2015-01-08 | 2015-01-15
Delivery Workgroup (#1) | DHS | In-progress |  |  | 2015-10-02 |  | 2015-10-16 | 2015-10-23 |  | 2015-11-06 | 2015-11-09 |  |  | 2015-12-04
Seamless Coverage Workgroup (#2) | DHS | In-progress |  |  | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-22 |  | 2015-11-06 | 2015-11-12 |  |  |  |  | 2015-12-17
Barriers to Access Workgroup (#3) | DHS | In-progress |  |  | 2015-10-02 | 2015-10-09 | 2015-10-16 | 2015-10-23 |  | 2015-11-06 | 2015-11-13 |  |  | 2015-12-04
Delivery Workgroup
Data Sharing Barriers
Discuss options and considerations for eliminating data sharing barriers | WG | In-progress
Identify preliminary recommendations on eliminating data sharing barriers | WG | In-progress
Present preliminary data sharing barriers recommendations to Task Force | WG | In-progress
Refine preliminary eliminating data sharing barriers recommendations | WG
Present final data sharing barriers recommendations to Task Force | WG
Prospective Assignment, Prospective Payment and Direct Contracting
Discuss options and considerations for payment system/direct contracting | WG | In-progress
Identify preliminary recommendations on payment system/direct contracting | WG | In-progress
Present preliminary payment system/direct contracting recommendations to Task Force | WG
Refine preliminary payment system/direct contracting recommendations | WG
Present final payment system/direct contracting to Task Force | WG
Seamless Coverage Workgroup
Draft priorities and map agendas | Manatt | Complete
Validate priorities and agendas | WG lead/DHS | Complete
Develop facilitation materials on: Options & Considerations for Seamless Coverage Continuum/Reducing Financial Barriers | Manatt | Complete
Develop facilitation materials on: Preliminary Recommendations for Seamless Coverage Continuum/Reducing Financial Barriers, Stable Marketplace Platform | Manatt | Complete
Develop facilitation materials on Consolidation, Alignment, Innovation and Market Stability | Manatt | Complete
Develop facilitation materials on Financing | Mantt | Complete
Develop facilitation materials on: Final Recommendations for Reducing Financial Barriers, Stable Marketplace Platform, Consolidation/Alignment/Innovation/Market Stability, Financing | Manatt
Financial Barriers/Seamless Coverage Continuum
Discuss options and considerations for reducing financial barriers | Joint with Barriers WG | Complete
Identify preliminary recommendations for reducing financial barriers | Joint with Barriers WG | Complete
Present preliminary financial barriers recommendations to Task Force | Joint with Barriers WG | Complete
Refine preliminary financial barriers recommendations | Joint with Barriers WG | In-progress
Present final financial barriers recommendations to Task Force | Joint with Barriers WG
Stable Marketplace Platform (MNsure governance)
Discuss options and considerations for stable Marketplace platform | WG | In-progress
Identify preliminary recommendations on stable Marketplace platform | WG | In-progress
Present preliminary recommendations for stable Marketplace platform | WG
Refine preliminary recommendations for stable Marketplace platform | WG
Present final recommendations forstable Marketplace platform to Task Force | WG
Consolidation, Alignment, Innovation and Market Stability
Discuss options and considerations for consolidation, alignment, innovation and market stability | WG | Complete
Identify preliminary recommendations on consolidation, alignment, innovation and market stability | WG | In-progress
Present preliminary recommendations for consolidation, alignment, innovation and market stability to Task Force | WG
Refine preliminary recommendations for consolidation, alignment, innovation and market stability | WG
Present final recommendations for consolidation, alignment, innovation and market stability to Task Force | WG
Financing a Seamless Coverage Continuum
Discuss options and considerations for financing | WG | In-progress
Identify preliminary recommendations on financing | WG |  | Did not complete financing presentation at 11/6 meeting
Present preliminary recommendations for financing to Task Force | WG
Refine preliminary recommendations for financing | WG
Present final recommendations for financing to Task Force | WG
Barriers to Access Workgroup
Draft priorities and map agendas | Manatt | Complete
Validate priorities and agendas | WG lead/DHS | Complete
Develop facilitation materials on: "Options & Considerations for Seamless Coverage Continuum/Reducing Financial Barriers, Part 1" | Manatt | Complete
Develop facilitation materials on: "Preliminary Recommendations for Seamless Coverage Continuum/Reducing Financial Barriers" "Options & Considerations for Reducing Structural Barriers, Part 1" | Manatt | Complete
Develop facilitation materials on "Options & Considerations for Reducing Structural Barriers, Part 2" | Manatt | Complete
Develop facilitation materials on "Preliminary Recommendations for Reducing Structural Barriers" | Manatt | Complete
Develop facilitation materials on: "Final Recommendations for Reducing Financial Barriers," "Final Recommendations for Reducing Structural Barriers" | Manatt
Financial Barriers/Seamless Coverage Continuum
Discuss options and considerations for reducing financial barriers | Joint with Seamless WG | Complete
Identify preliminary recommendations for reducing financial barriers | Joint with Seamless WG | Complete
Present preliminary financial barriers recommendations to Task Force | Joint with Seamless WG | Complete
Refine preliminary financial barriers recommendations | Joint with Seamless WG | In-progress
Present final financial barriers recommendations to Task Force | Joint with Seamless WG
Structural Barriers
Discuss options and considerations for reducing structural barriers | WG | Complete
Identify preliminary recommendations on reducing structural barriers | WG | In-progress
Present preliminary structural barriers recommendations to Task Force | WG
Refine preliminary structural barriers recommendations | WG
Present final structural barriers recommendations to Task Force | WG
Task Force
Financial Barriers/Seamless Coverage Continuum
Provide feedback on preliminary recommendations | Task Force | In-progress
Approve final recommendations | Task Force
MNSure Governance
Provide feedback on preliminary recommendations | Task Force
Approve final recommendations | Task Force
Minnesota Coverage Programs Financing
Provide feedback on preliminary recommendations | Task Force
Approve final recommendations | Task Force
Structural Barriers
Provide feedback on preliminary recommendations | Task Force
Approve final recommendations | Task Force
Actuarial Modeling
Review actuarial modeling | Milliman |  | Milliman meeting scheduled for week of 11/9; Milliman to present to WG and Task Force on 11/13
Recommendations Report
Draft outline of report | Manatt | In-progress
Develop first draft | Manatt
Develop second draft | Manatt
Conduct actuarial analysis of options | Milliman
Develop third draft | Manatt
Finalize report (if revised final recommendations differ) | Manatt
Submit report to Legislature/Governor | Task Force | [18 empty] | 2015-01-15
Project Management
Expand and finalize project work plan | Manatt | Complete
Conduct weekly Manatt/DHS meeting | Manatt/DHS | In-progress
Conduct pre-call with Task Force/workgroup leads | Manatt/DHS | In-progress | Scheduled weekly
Conduct weekly internal meeting | Manatt | In-progress | Scheduled weekly
Draft takeaways | Manatt | In-progress

## Meeting Schedule - Graphical
|  | 2015-01-01 |  | 2015-01-02 |  |  | Key
October | CT | 2015-10-01 |  | 2015-10-02 | IN-PERSON | - ST. PAUL | Barriers WG meeting
2015 | 8-9a |  |  |  | Barriers/ Seamless |  | Seamless WG meeting
| 9-10 |  |  |  | JOINT (8:30-11) | Delivery | Barriers/Seamless WG joint meeting
| 10-11 |  |  |  |  | (9:30-11:30)
| 11-12p | [5 empty] | Task Force meeting
| 12-1 |  |  |  | Task Force | (12-3) | All times CT
1-2
2-3
|  | 2015-10-08 |  | 2015-10-09 | VIRTUAL | (or in-person)
| 8-9a |  |  |  | Barriers
| 9-10 |  |  |  | (8:30-10)
| 10-11 |  |  |  | Barriers and Seamless JOINT | (10-11)
| 11-12p |  |  |  |  | Seamless
| 12-1 |  |  |  |  | (11-1:00)
1-2
2-3
|  | 2015-10-15 |  | 2015-10-16 | VIRTUAL | (or in-person)
| 8-9a |  |  |  | Barriers (8:30-11) | Delivery (8-9)
9-10
10-11
11-12p
12-1
| 1-2 |  |  |  | Seamless
| 2-3 |  |  |  | (1-3)
|  | 2015-10-22 |  | 2015-10-23 | IN-PERSON | - ROCHESTER
8-9a
| 9-10 |  |  |  | Barriers | Delivery
| 10-11 |  |  |  | (9-11) | (9:30-11:30)
11-12p
| 12-1 |  | IN-PERSON - ST. PAUL/ROCHESTER? |  | Task Force | (12-3)
| 1-2 |  | Seamless
| 2-3 |  | (1-3)
|  | 2015-10-29 |  | 2015-10-30
8-9a
9-10
10-11
11-12p
12-1
1-2
2-3
November |  | 2015-11-05 |  | 2015-11-06 | VIRTUAL | (or in-person)
2015 | 8-9a |  |  |  | Barriers
| 9-10 |  |  |  | (8:30-10)
| 10-11 |  |  |  | Barriers and Seamless JOINT | (10-11)
| 11-12p |  |  |  |  | Seamless
| 12-1 |  |  |  |  | (11-12:30)
1-2
| 2-3 |  |  |  | Delivery
| 3-4 |  |  |  | (2-4)
|  | 2015-11-12 |  | 2015-11-13 | IN-PERSON | - ST. CLOUD?
8-9a
| 9-10 |  |  |  | Barriers
| 10-11 |  |  |  | (9-11)
| 11-12p |  | IN-PERSON - ST. PAUL
| 12-1 |  | Seamless |  | Task Force | (12-3)
| 1-2 |  | (12-3)
2-3
|  | 2015-11-19 |  | 2015-11-20
8-9a
9-10
10-11
| 11-12p |  |  |  | Barriers
| 12-1 |  |  |  | (11-1)
1-2
2-3
|  | 2015-11-26 |  | 2015-11-27
THANKSGIVING
December |  | 2015-12-03 |  | 2015-12-04 | IN-PERSON - | ST. PAUL
2015 | 8-9a |  |  |  | Barriers (8-10) | Delivery (8-9)
| 9-10 |  |  |  |  | Seamless
| 10-11 |  |  |  |  | (9-12)
11-12p
| 12-1 |  |  |  | Task Force | (12-3)
1-2
2-3
|  | 2015-12-10 |  | 2015-12-11
8-9a
9-10
10-11
11-12p
12-1
1-2
2-3
|  | 2015-12-17 |  | 2015-12-18 | IN-PERSON - | ST. PAUL
8-9a
9-10
10-11
11-12p
| 12-1 |  | IN-PERSON - ST. PAUL |  | Task Force | (12-3)
| 1-2 |  | Seamless
| 2-3 |  | (1:30-3)
|  | 2015-12-24 |  | 2015-12-25
CHRISTMAS
|  | 2015-12-31 |  | 2016-01-01
NEW YEAR'S
January |  | 2016-01-07 |  | 2016-01-08 | IN-PERSON - | ST. PAUL
2015 | 8-9a
9-10
10-11
11-12p
| 12-1 |  |  |  | Task Force | (12-3)
1-2
2-3
|  | 2016-01-14 |  | 2016-01-15
8-10a
10a-12p
| 12-2p |  |  |  | Task Force | (12-3)
2-4p
4-6p
Note on F49: Note - Delivery is also meeting on 11/9, 2-4PM CT, Virtually
Note on G91: Note: 2 Manatt participants virtually
Note on G105: Note: 2 Manatt participants virtually
Note on G111: Note: 2 Manatt participants virtually

## Meeting Schedule - Text
Health Care Financing Task Force - Master Schedule (as of 11/8/15)
Meeting Type | Day | Time (CT) | Modality (Virtual/In-Person) | Manatt Participation | Topics/Deliverables
Barriers Workgroup | Friday, October 2 | 8:30-11:00 am | In person (joint with Seamless) | In person | Options & Considerations for reducing financial barriers/seamless coverage continuum
Seamless Workgroup | Friday, October 2 | 8:30-11:00 am | In person (joint with Barriers) | In person | Options & Considerations for reducing financial barriers/seamless coverage continuum
Delivery Workgroup | Friday, October 2 | 9:30-11:30 am | In person | In person | Development of Integrated Care Models/Value-based Purchasing
Task Force | Friday, October 2 | 12:00-3:00 pm | In person | In person | Workgroup report outs State policy tools: 1332, 1115, etc.
Barriers Workgroup | Friday, October 9 | 8:30-11:00am | In person/Virtual Recorded Webinar for members (partial joint session/Seamless) | Virtual | Options & Considerations for Reducing Structural Barriers, Part 1 (differences in benefits, plans, providers and managing transitions) Preliminary Recommendations for reducing financial barriers/seamless coverage continuum
Seamless Workgroup | Friday, October 9 | 10:00-1:00 pm | In person/Virtual Recorded Webinar for members (partial joint session/Barriers) | In person | Preliminary Recommendations for reducing financial barriers/seamless coverage continuum Options & Considerations for Ensuring a Stable Marketplace and Coverage Platform (Mnsure/Marketplace)
Delivery Workgroup | Friday, October 16 | 8:00-9:00 am | Virtual |  | Options & Considerations for eliminating barriers to data sharing that impact the care continuum
Barriers Workgroup | Friday, October 16 | 8:30-11:00 am | In person/Virtual Recorded Webinar | Virtual | Review Preliminary Recommendations for Reducing Financial Barriers: affordability scale, standard benefit design Discuss Preliminary Recommendations for Reducing Structural Barriers and Disparities: benefit alignment Testimony on disparitites
Seamless Workgroup | Friday, October 16 | 1:00-3:00 pm | In person for members | Virtual | Options & Considerations for Ensuring a Stable Marketplace and Coverage Platform (Mnsure/Marketplace) (cont'd)
Seamless Workgroup | Thursday, October 22 | 1:00-3:00 pm | In person | In person | Review Preliminary Recommendations for Ensuring a Stable Marketplace and Coverage Platform (MNsure/Marketplace) Options & Considerations for Consolidation, Alignment, and Innovation to Achieve Seamlessness & Market Stability -Aligning eligibility rules, benefits, and plans -Ensuring a stable coverage continuum, including the private market
Delivery Workgroup | Friday, October 23 | 9:30-11:30 am | In person (Rochester) |  | Options, Considerations and Preliminary Recommendations for eliminating barriers to data sharing that impact the care continuum
Barriers Workgroup | Friday, October 23 | 9:00-11:00 am | In person (Rochester) | In person | Review Joint Preliminary Recommendations on Financial Barriers Review Preliminary Recommendations for Reducing Structural Barriers: affordability scale, standard benefit design, benefit alignment Options & Considerations for Reducing Structural Barriers and Disparities, Part 3 (disparities in access due to language, culture, health literacy)
Task Force | Friday, October 23 | 12:00-3:00 pm | In person (Rochester) | In person | Alternative Coverage Options (VT) Value Based Purchasing Update on Marketplace/Mnsure issues and Seamlessness Workgroup discussions Joint Recommendations on Financial Barriers/Seamless Coverage Continuum
Barriers Workgroup | Friday, November 6 | 8:30-11:00am | In person/Virtual Recorded Webinar for members (partial joint session/Seamless) | Virtual | Discuss Rural Health Access Issues and discuss preliminary recommendations. Review Options, Considerations and Preliminary Recommendations on: • Consumer assistance/health literacy • Provider/plan alignment • Plan design • Benefits alignment Discuss Path to Final Recommendations (joint with Seamless)
Seamless Workgroup | Friday, November 6 | 10:00am-1:00 pm | In person/Virtual Recorded Webinar (partial joint session/Barriers) | Virtual | Discuss Path to Final Recommendations (joint with Barriers) Discuss Premium Stability Issues and preliminary recommendations Options & Considerations for Financing a Sustainable & Seamless Coverage Continuum (MA, MinnesotaCare, MNsure)
Delivery Workgroup | Friday, November 6 | 2:00-4:00 pm | Virtual |  | Finalize preliminary recommendations on eliminating or reducing data-sharing barriers to ensure seamless care. Enhancing care delivery across care continuum through alternate payment arrangements with providers across public programs and commercial markets, potentially including: • Impact of payment models on care delivery, health disparities, and safety-net and rural providers • Identification of challenges and areas for enhancement of payments to support integration of care • Continued expansion and alignment of payment models across markets, including public and private • Short-term and long-term considerations for implementing care delivery model reforms in Minnesota Potential options for enhancements to payments that support integrated care delivery, may include, but is not limited to: • Direct contracting opportunities with providers to enhance care delivery and reduce health disparities • Accountable Care, Health Care Homes, or other models that incent care delivery through enhanced payment, risk arrangements or other mechanisms • Prospective payment models that support Integrated Care Delivery and reduce health disparities • Enhanced attribution of patients to primary care providers through a prospective model
Delivery Workgroup | Monday, November 9 | 2:00-4:00 pm | Virtual |  | Continue discussions on enhancing and accelerating coordinated care delivery systems and payment reforms Develop preliminary recommendations to enhance care delivery across care continuum through alternate payment arrangements with providers across public programs and commercial markets
Seamless Workgroup | Thursday, November 12 | 12:00-3:00 pm | In person | In person | Review Preliminary Recommendations on Premium Stability (as necessary) Review Preliminary Recommendations for Financing a Sustainable & Seamless Coverage Continuum (MA, MinnesotaCare, MNsure) Review Preliminary Recommendations on Ensuring a Stable Marketplace and discuss and refine Marketplace recommendation: Marketplace goals, narrow Marketplace options, and identify next steps for developing framework for OEP 3 evaluation Review modeling approach for: • Smoothing the Cliff • Alignment/Consolidation of MinnesotaCare • Family Glitch
Barriers Workgroup | Friday, November 13 | 9:00-11:00am | In person (St. Cloud) | In person | Review and refine Preliminary Recommendations on Reducing Structural Barriers and Disparities: • Consumer assistance/health literacy • Plan design • Benefits alignment • Rural health (if any) Review and finalize Affordability Scale Review modeling approach for: • Affordability Scale/Smoothing the Cliff • Benefits Alignment
Task Force | Friday, November 13 | 12:00-3:00 pm | In person (St. Cloud) | In person | Panel Presentation Preliminary Recommendations • Ensuring a Stable Marketplace and Coverage Platform (Seamless) • Reducing Structural Barriers and Disparities (Barriers) • Reducing Data-Sharing Barriers to Improve Care Continuum (Delivery) • Directional Guidance on Enhancements to Payment Model(s) that Support Integrated Care (Delivery) Milliman: review modeling approach
Delivery Workgroup | Friday, December 4 |  |  |  | Review Milliman modeling results Refine Preliminary Recommendations : • Reducing Data-Sharing Barriers to Improve Care Continuum • Directional Guidance on Enhancements to Payment Model(s) that Support Integrated Care
Barriers Workgroup | Friday, December 4 | 9:00-11:00am | In person | In person | Affordability Scale/Smoothing the Cliff (Joint with Seamless) Refine Preliminary Recommendations on Affordability Scale/Smoothing the Cliff (Joint with Seamless) Review Milliman modeling results for Benefits Alignment Refine Preliminary Recommendations on Benefits Alignment Refine Remaining Preliminary Recommendations on Structural Barriers: • Consumer assistance/health literacy • Plan design • Rural health (if any)
Seamless Workgroup | Friday, December 4 | 10:00am-12:00pm | In person | In person | Review Milliman modeling results for Affordability Scale/Smoothing the Cliff (Joint with Barriers) Refine Preliminary Recommendations on Affordability Scale/Smoothing the Cliff (Joint with Barriers) Review Milliman modeling results for Alignment/Consolidation of Minnesota Care Refine Preliminary Recommendations on Alignment/Consolidation of MinnesotaCare
Task Force | Friday, December 4 | 12:00-3:00 pm | In person | In person | Preliminary Recommendations: (1) Financing a Seamless Coverage Continuum, (2) Ensuring a Stable Marketplace and Coverage Platform, and (3) Opportunities for Consolidation, Alignment and Innovation.
Seamless Workgroup | Thursday, December 17 | 1:00 pm-3:00 pm | In person | Virtual | Review Milliman modeling results on Financing a Sustainable & Seamless Coverage Continuum (MA, MinnesotaCare, MNsure) Refine Preliminary Recommendations on Financing a Seamless Coverage Continuum (MA, MinnesotaCare, MNsure)
Task Force | Friday, December 18 | 12:00-3:00 pm | In person | Virtual | Final Recommendations from workgroups, Part 1 Examine impact of recommendations on Triple Aim and health disparities PLACEHOLDER FOR POTENTIAL DATA FROM COMMERCE on their options
Task Force | Friday, January 8 | 12:00-3:00 pm | In person | Virtual | Final Recommendations from workgroups, Part 2 Review and refine Final Recommendations & Draft Report
Task Force | Friday, January 15 | 12:00-3:00 pm | In person | Virtual | Review and approve final report Presentation of Final Report and Recommendations to the Legislature and Governor
Note on F21: Stacie Weeks: Given the short amount of time and the points made by many of the members, we should get the work of this workgroup finished before picking up the commerce pieces again. This also gives them more time to finish their analyses. If they aren’t finished then members can decide if they want to tell the Governor and Legislature that these topics deserve attention next session or longer-term
Note on A27: Alice Lam: Consider deferring 12/4 meeting to allow workgroups more time for deliberation on recommendations.
Note on F29: Stacie Weeks: Given the short amount of time and the points made by many of the members, we should get the work of this workgroup finished before picking up the commerce pieces again. This also gives them more time to finish their analyses. If they aren’t finished then members can decide if they want to tell the Governor and Legislature that these topics deserve attention next session or longer-term

## Running List of Recommendations
HEALTH CARE FINANCING TASK FORCE RECOMMENDATIONS |  | Updated: 11/12/15 |  | COMPLIANCE WITH TASK FORCE LEGISLATION | COMPLIANCE WITH TASK FORCE LEGISLATION
RECOMMENDATION AREA | POTENTIAL RECOMMENDATION | STATUS | WORKGROUP | OPTIONS EXPLORED | GOALS ADDRESSED
Affordability: Ensuring affordable coverage and care | Establish a Minnesota tailored health coverage affordability scale to guide policy, program, and financing decisions with regard to Minnesota’s coverage continuum | For further consideration by Barriers WG on 11/13; present preliminary recommendation to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
| Rationalize affordability definition for families with access to employer sponsored insurance (ESI) (i.e., fix the family glitch) | Preliminary recommendation presented to HCFTF on 10/23; further deliberation by Seamless workgroup pending modeling results | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
| Require standard Qualified Health Plan (QHP) offerings in the Marketplace to improve consumer choice and experience, including ensuring availability of no or low deductible plans: (1) Create standard cost-sharing designs – including low and no deductible plan options – and require carriers offer standard products in addition to other products they choose to offer (2) Limit the number of non-standard cost sharing designs to reduce consumer confusion with product offerings (3) Exempt certain services from deductibles to incentivize utilization of primary care and generic prescription drugs | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
| Create benefit alignment across the coverage continuum and provide access to high value benefits: (1) Add adult dental benefits in QHPs through MNsure on par with Medical Assistance and MinnesotaCare Note: MA and MinnesotaCare beneficiaries with dental benefits may still experience barriers to access due to transportation and dental provider shortages. (2) Provide all or some unique Medical Assistance benefits through MinnesotaCare, such as non-emergency medical transportation | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13; for further deliveration after Milliman modeling results | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: c. Alignment and alternatives to benefit sets | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage;
| Improve and enhance community based consumer assistance resources: (1) Develop expanded community based, consumer assistance capacity to support consumers in accessing health coverage, understanding how to use their health coverage, and addressing social determinants of health (e.g., food and nutrition, housing) (2) Provide adequate and timely payment to, and appropriate training for, community based consumer assisters (3) Utilize currently available race/ethnicity/ data to identify type and level of consumer needs and target deployment of consumer assistance resources (4) Ensure that the state’s selection of Navigators prioritizes entities able to provide linguistically and culturally appropriate assistance | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage; (4) assessing the impact of options for innovation on their potential to reduce health disparities
Seamlessness: Smoothing MN affordability cliff and other program requirements | Explore options to reduce the financial affordability cliff in premiums, cost-sharing and deductibles for health coverage at 200% FPL: (1) Establish voluntary accounts for Medical Assistance and MinnesotaCare enrollees to offset current or future premiums/cost-sharing for health insurance coverage, earn monetary rewards for wellness activities (2) Smooth cliff by expanding eligibility for enhanced subsidies to consumers with incomes 200-275% FPL (pre-ACA MinnesotaCare eligibility levels) **Consider various funding mechanisms including redistributing federal subsidies (advanced premium tax credits and cost-sharing reductions) to improve affordability for consumers with incomes 200-300% FPL; maximizing federal Medicaid funding | Preliminary recommendation presented to HCFTF on 10/23; further deliberation by Seamless and Barriers workgroups pending modeling results | Seamless and Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
Coverage: Define coverage program options for the coverage continuum with agreed upon levels up to 275% FPL | Align insurance affordability programs including eligibility and enrollment rules, benefits and plan requirements: (1) Explore consolidation of Medical Assistance and MinnesotaCare: a) One public program up to 275% FPL; OR b) One program up to 200% FPL with a subsidy program for premiums and cost-sharing from 200-to-275% FPL for defined QHP products (2) Explore consolidation of the MinnesotaCare with the private Marketplace population and providing additional subsidies for the purchase of defined QHP products (138- 275% FPL) (3) Maintain Status Quo on MinnesotaCare For long-term consideration, outside of the scope of Task Force recommendations for January 15th: (1) Transition to a Single Payer Program Model (2) Consolidate All Programs in the Private Marketplace | For further consideration by Seamless WG pending modeling results; present preliminary recommendation to HCFTF on 11/13 | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: a. Alignment of eligibility and enrollment requirements; b. Smoothing consumer cost-sharing across programs; c. Alignment and alternatives to benefit sets; f. Alternatives to APTCs; g. Alternatives to QHPs (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform | (1) seamless consumer experience across all programs; (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; and (7) increasing transparency and accountability of program operations.
Financing: Evaluate options for revenue sources to fund coverage continuum |  | For discussion during 11/12 Seamless WG | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP (broadly) | (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; (7) increasing transparency and accountability of program operations.
Future of Mnsure: Narrow options | Develop framework to evaluate 2016 OEP performance to inform future decisionmaking on the Marketplace and a framework to evaluate the current Marketplace model against other options for Minnesota: (1) SBM (stay the course) (2) Supported SBM (3) Partially Privatized SBM (4) FFM | For further consideration by Seamless WG to further define Minnesota goals for its Marketplace and narrow the Marketplace options; present preliminary recommendation to HCFTF on 11/13 | Seamless | (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform | (1) seamless consumer experience across all programs; (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; and (7) increasing transparency and accountability of program operations.
Sustainability of IAP Costs: Develop recommendation for advancing delivery system and payment reform | Make technical updates and clarifications to Minnesota’s Health Records Act to leave a patient’s ability to specify how their information can be shared intact but allow patient consent preferences to be more easily operationalized at the provider level. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery | (2) reducing barriers to accessibility and affordability of coverage; (6) promoting effectively and efficiently aligning program resources and operations
| Provide ongoing education and technical assistance to health and health care providers and patients, about state and federal laws that govern how clinical health information can be stored, used, and shared, and about best practices for appropriately securing information and preventing inappropriate use. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Conduct a broad study on the appropriate future structure, legal/regulatory framework, financing, and governance for HIE in Minnesota, building on lessons from other states and countries. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore these options in further discussion: 1) Dependent on results of HIE study, consider other modifications to Minnesota’s Health Records Act, to align with federal HIPAA standards or to update opt-in or opt-out requirements. 2) Support expanded health information technology capabilities (ex. EHRs) in a broad range of care settings, to enable smaller and specialty providers to participate in HIE. 3) Consider developing a funding mechanism for core HIE transactions, such as admission/discharge/transfer alerts, care summaries, or care plans, to ensure basic information can be exchanged statewide. 4) Support the establishment of robust, sustainable HIE “shared services,” such as consent management, that would be available statewide through a central vendor. |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for how payment models that support and encourage enhanced integrated care can address health disparities |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for encouraging/incentivizing payment models that support and encourage enhanced integrated care with providers across public programs and commercial markets |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for enhancement and acceleration of current and new delivery system and payment reform models (e.g., prospective payment, assignment) |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
Stability of the MN Marketplace | Explore options to stabilize Marketplace premiums: (1) Create Minnesota-specific price stability mechanisms (e.g., reinsurance) (2) Merge individual and small group markets (3) Closer scrutiny of insurer profits (4) Cost transparency | For further consideration by Seamless WG, following Commerce modeling results | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs (3) Options for alignment, consolidation, and governance of certain operational components, including, but not limited to: a. MNsure | (2) reducing barriers to accessibility and affordability of coverage; (7) increasing transparency and accountability of program operations.

## Barriers Recommendations
HEALTH CARE | FINANCING TASK FORCE RECOMMENDATIONS | Updated: 11/12/15 |  | COMPLIANCE WITH TASK FORCE LEGISLATION | COMPLIANCE WITH TASK FORCE LEGISLATION
RECOMMENDATION AREA | POTENTIAL RECOMMENDATION | STATUS | WORKGROUP | OPTIONS EXPLORED | GOALS ADDRESSED
Affordability: Ensuring affordable coverage and care | Establish a Minnesota tailored health coverage affordability scale to guide policy, program, and financing decisions with regard to Minnesota’s coverage continuum | For further consideration by Barriers WG on 11/13; present preliminary recommendation to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
| Require standard Qualified Health Plan (QHP) offerings in the Marketplace to improve consumer choice and experience, including ensuring availability of no or low deductible plans: (1) Create standard cost-sharing designs – including low and no deductible plan options – and require carriers offer standard products in addition to other products they choose to offer (2) Limit the number of non-standard cost sharing designs to reduce consumer confusion with product offerings (3) Exempt certain services from deductibles to incentivize utilization of primary care and generic prescription drugs | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
| Create benefit alignment across the coverage continuum and/or provide access to high value benefits: (1) Add adult dental benefits in QHPs through MNsure on par with Medical Assistance and MinnesotaCare Note: MA and MinnesotaCare beneficiaries with dental benefits may still experience barriers to access due to transportation and dental provider shortages. (2) Provide non-emergency medical transportation as a covered benefit in MinnesotaCare | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13; for further deliveration after Milliman modeling results | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: c. Alignment and alternatives to benefit sets | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage;
| Improve and enhance community based consumer assistance resources: (1) Develop expanded community based, consumer assistance capacity to support consumers in accessing health coverage, understanding how to use their health coverage, and addressing social determinants of health (e.g., food and nutrition, housing) (2) Provide adequate and timely payment to, and appropriate training for, community based consumer assisters (3) Utilize currently available data on the remaining uninsured, including race/ethnicity data, to identify type and level of consumer needs and target deployment of consumer assistance resources (4) Ensure that the state’s selection of Navigators prioritizes entities able to provide linguistically and culturally appropriate assistance by developing selection criteria targeted to these core capacities | Under consideration by Barriers; to be validated and refined the week of 11/9, and potentially presented to to HCFTF on 11/13 | Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage; (4) assessing the impact of options for innovation on their potential to reduce health disparities
Seamlessness: Smoothing MN affordability cliff and other program requirements | Explore options to reduce the financial affordability cliff in premiums, cost-sharing and deductibles for health coverage at 200% FPL: (1) Establish voluntary accounts for Medical Assistance and MinnesotaCare enrollees to offset current or future premiums/cost-sharing for health insurance coverage, earn monetary rewards for wellness activities (2) Smooth cliff by expanding eligibility for enhanced subsidies to consumers with incomes 200-275% FPL (pre-ACA MinnesotaCare eligibility levels) **Consider various funding mechanisms including redistributing federal subsidies (advanced premium tax credits and cost-sharing reductions) to improve affordability for consumers with incomes 200-300% FPL; maximizing federal Medicaid funding | Preliminary recommendation presented to HCFTF on 10/23; further deliberation by Seamless and Barriers workgroups pending modeling results | Seamless and Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage

## Seamless Recommendations
HEALTH CARE FINANCING | TASK FORCE RECOMMENDATIONS | Updated: 11/12/15 |  | COMPLIANCE WITH TASK FORCE LEGISLATION | COMPLIANCE WITH TASK FORCE LEGISLATION
RECOMMENDATION AREA | POTENTIAL RECOMMENDATION | STATUS | WORKGROUP | OPTIONS EXPLORED | GOALS ADDRESSED
Affordability: Ensuring affordable coverage and care | Rationalize affordability definition for families with access to employer sponsored insurance (ESI) (i.e., fix the family glitch) | Preliminary recommendation presented to HCFTF on 10/23; further deliberation by Seamless workgroup pending modeling results | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
Seamlessness: Smoothing MN affordability cliff and other program requirements | Explore options to reduce the financial affordability cliff in premiums, cost-sharing and deductibles for health coverage at 200% FPL: (1) Establish voluntary accounts for Medical Assistance and MinnesotaCare enrollees to offset current or future premiums/cost-sharing for health insurance coverage, earn monetary rewards for wellness activities (2) Smooth cliff by expanding eligibility for enhanced subsidies to consumers with incomes 200-275% FPL (pre-ACA MinnesotaCare eligibility levels) **Consider various funding mechanisms including redistributing federal subsidies (advanced premium tax credits and cost-sharing reductions) to improve affordability for consumers with incomes 200-300% FPL; maximizing federal Medicaid funding | Preliminary recommendation presented to HCFTF on 10/23; further deliberation by Seamless and Barriers workgroups pending modeling results | Seamless and Barriers | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs | (1) seamless consumer experience across all programs; (2) reducing barriers to accessibility and affordability of coverage
Coverage: Define coverage program options for the coverage continuum with agreed upon levels up to 275% FPL | Align insurance affordability programs including eligibility and enrollment rules, benefits and plan requirements: (1) Explore consolidation of Medical Assistance and MinnesotaCare: a) One public program up to 275% FPL; OR b) One program up to 200% FPL with a subsidy program for premiums and cost-sharing from 200-to-275% FPL for defined QHP products (2) Explore consolidation of the MinnesotaCare with the private Marketplace population and providing additional subsidies for the purchase of defined QHP products (138- 275% FPL) (3) Maintain Status Quo on MinnesotaCare For long-term consideration, outside of the scope of Task Force recommendations for January 15th: (1) Transition to a Single Payer Program Model (2) Consolidate All Programs in the Private Marketplace | For further consideration by Seamless WG pending modeling results; present preliminary recommendation to HCFTF on 11/13 | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: a. Alignment of eligibility and enrollment requirements; b. Smoothing consumer cost-sharing across programs; c. Alignment and alternatives to benefit sets; f. Alternatives to APTCs; g. Alternatives to QHPs (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform | (1) seamless consumer experience across all programs; (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; and (7) increasing transparency and accountability of program operations.
Financing: Evaluate options for revenue sources to fund coverage continuum |  |  | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP (broadly) | (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; (7) increasing transparency and accountability of program operations.
Future of Mnsure: Narrow options | Develop framework to evaluate 2016 OEP performance to inform future decisionmaking on the Marketplace and a framework to evaluate the current Marketplace model against other options for Minnesota: (1) SBM (stay the course) (2) Supported SBM (3) Partially Privatized SBM (4) FFM | For further consideration by Seamless WG to further define Minnesota goals for its Marketplace and narrow the Marketplace options; present preliminary recommendation to HCFTF on 11/13 | Seamless | (2) Options for alignment, consolidation, and governance of certain operational components: a. MNsure; b. Program eligibility; c. Program enrollment; d. Call centers; e. Contracting; and f. Shared eligibility IT platform | (1) seamless consumer experience across all programs; (3) improving sustainable financing of health programs, including impact on the state budget; (6) promoting effectively and efficiently aligning program resources and operations; and (7) increasing transparency and accountability of program operations.
Stability of the MN Marketplace | Explore options to stabilize Marketplace premiums: (1) Create Minnesota-specific price stability mechanisms (e.g., reinsurance) (2) Merge individual and small group markets (3) Closer scrutiny of insurer profits (4) Cost transparency | For further consideration by Seamless WG, following Commerce modeling results | Seamless | (1) Options for providing and financing seamless coverage for persons otherwise eligible for IAP: b. Smoothing consumer cost-sharing across programs (3) Options for alignment, consolidation, and governance of certain operational components, including, but not limited to: a. MNsure | (2) reducing barriers to accessibility and affordability of coverage; (7) increasing transparency and accountability of program operations.

## Delivery Design Recommendations
HEALTH CARE FINANCING | TASK FORCE RECOMMENDATIONS | Updated: 11/12/15 |  | COMPLIANCE WITH TASK FORCE LEGISLATION | COMPLIANCE WITH TASK FORCE LEGISLATION
RECOMMENDATION AREA | POTENTIAL RECOMMENDATION | STATUS | WORKGROUP | OPTIONS EXPLORED | GOALS ADDRESSED
Sustainability of IAP Costs: Develop recommendation for advancing delivery system and payment reform | Make technical updates and clarifications to Minnesota’s Health Records Act to leave a patient’s ability to specify how their information can be shared intact but allow patient consent preferences to be more easily operationalized at the provider level. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery | (2) reducing barriers to accessibility and affordability of coverage; (6) promoting effectively and efficiently aligning program resources and operations
| Provide ongoing education and technical assistance to health and health care providers and patients, about state and federal laws that govern how clinical health information can be stored, used, and shared, and about best practices for appropriately securing information and preventing inappropriate use. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Conduct a broad study on the appropriate future structure, legal/regulatory framework, financing, and governance for HIE in Minnesota, building on lessons from other states and countries. | Being considered at the 11/6 WG meeting; present preliminary recommendation to HCFTF on 11/13 | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore these options in further discussion: 1) Dependent on results of HIE study, consider other modifications to Minnesota’s Health Records Act, to align with federal HIPAA standards or to update opt-in or opt-out requirements. 2) Support expanded health information technology capabilities (ex. EHRs) in a broad range of care settings, to enable smaller and specialty providers to participate in HIE. 3) Consider developing a funding mechanism for core HIE transactions, such as admission/discharge/transfer alerts, care summaries, or care plans, to ensure basic information can be exchanged statewide. 4) Support the establishment of robust, sustainable HIE “shared services,” such as consent management, that would be available statewide through a central vendor. |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for how payment models that support and encourage enhanced integrated care can address health disparities |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for encouraging/incentivizing payment models that support and encourage enhanced integrated care with providers across public programs and commercial markets |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations
| Explore options for enhancement and acceleration of current and new delivery system and payment reform models (e.g., prospective payment, assignment) |  | Delivery Design | (2) Options for transforming health care purchasing and delivery a. Expansion of value-based direct contracting with providers and other entities to reward improved health outcomes and reduced costs, including selective contracting; b. Contracting to provide services to public programs and commercial products; and c. Payment models that support and reward coordination of care across the continuum of services and programs | (2) reducing barriers to accessibility and affordability of coverage; (3) improving sustainable financing of health programs, including impact on the state budget; (4) assessing the impact of options for innovation on their potential to reduce health disparities; (5) expanding innovative health care purchasing and delivery systems strategies that reduce cost and improve health; (6) promoting effectively and efficiently aligning program resources and operations